## 2021-22
Patent and Technology License Committee
Action Plan 2021/2022
Item | Deliverable | Responsible | Status/Remarks
1- Strengthen the Committee organization
1.1- Renew the Committee working team and build a true Committee membership | The opportunity and the feasibility to get more members in the committee with specific portfolio responsibility | Committee Members | see https://connect.lesi.org/home
|  | Vice Chairs | Qinghong Xu (LES China), Claudia Tapia (LES Germany, Ericsson); Jennifer Pierce (LES Britain & Ireland)
Role and responsibilities of Committee members |  |  | To identify specific projects and/or portfolio's for each committee member project Champions
Kids IP Day
Annual presentation 17 March 2022 | Celebrate Kids IP Day | M Kleyn, Roberto Dini and Federica Brotto | Updating material and prepare for March 17th use - luanch templates to societies end of Feb 2022
After math LESI AGM - Topics
FTO - what does it mean today - follow-up webinar from LESI AGM |  | Nikos/Madelein | Planned for 2022
Trade Secret Panel: Licensing of Know-how and trade secret - Les Nouvelle live |  | Jenny Pierce/Madelein Kleyn | Completed July 2021
LESI AGM - 2022
Three proposal submitted |  | Madelein Kleyn, Nikos Minas, Chyreene Truluck | Energy sector, Life Science Sector, Tax
Contribution to publications
Patent Pooling | Over two editions - starting Sept 2021 | Claudia Tapia | Claudia, please send me the documents you wish to publish for review and proposal to the editorial board for Les Nouvelle. Deadline for September issue is July 1st, The deadline for the December issue is October 1. - Standing over to 2022
Freedom to Operate | September edition | Madelein Kleyn | Published December 2021 edition
| December edition | Candida Ribeiro Caffe | Published Dec 2021
Covid pandemic and IP waivers | July/September | Madelein Kleyn | Published June 2021
Special edition - Laws affecting commercialisation of IP: Scoping of content for publication in Les Nouvelles and follow-up seminars | TBA | Jennifer Pierce/M Kleyn | TBA
Collaboration with other LESI Committees
Financial Modelling course | Better marketing of the LESI-Moolman training in collaboration with Education and IP Valuation Committees | M Kleyn | Can we list specific committees and specific collaborative efforts - webinar on IP Valuation as part of World IP Day - Continuing
Development of Course material for IP Valuation and legal aspects | collaboration with Education and IP Valuation Committees | M Kleyn/A Gorius/S Moolman | In Progress
Liasion with Copyright Licensing Committee |  | Jenny Pierce | Please provide specific plans for the year -
Committee members to include any other collaboration efforts for the year
Webinars: Conferences and Training
Participating and contributing teaching and training workshops. | The SME/start-up company journey to patent monetisation (e.g. through licensing) : Collaborative effort with LESI committees in a series of webinars for SME with experts guide SMEs through the various elements of IP commercialisation. We could even think of having an IP licensing help-desk, where SME post their enquiries and receive back an advise from an IP licensing expert. | Nikos Minas/Madelein Kleyn/ | Defining specific topics, speakers and timeline for deliverables during latter part of 2021/22
World IP Day 2022 |  | All - call for suggestions | World IP Day celebrations on 26 April 2022
IP and Transfer pricing: Inter-company licenses | Arrange a webinar with expert speakers addressing the topic of tax, and Transfer pricing - the risks and rewards | Madelein Kleyn | Will be scheduled in 2022
IP Toolkit
IP licensing help-desk, where SME post their enquiries and receive back an advise from an IP licensing expert. |  | Nikos Minas | Please advise plan for implementation
Create with other members a practical guidance on patent pools. |  | Claudia Tapia | Please advise plan for implementation
Practicial guide for Entrepreneurs in collaboration with universities |  | Derick Swart /Krystian Maciaszek | Please advise plan for implementation